## Slide 1
Notes: Chapter 7 Managing Risk

## Slide 2: Where We Are Now
Notes: To put the processes discussed in this chapter in proper perspective one should recognize that project managers must engage in risk management activities to compensate for the uncertainty inherent in project selection, management and project planning.
Although risk assessment may depend on subjective judgment, standard methods for identifying, assessing, and responding to risks should be included in all projects. Contingency plans increase the chance that the project can be completed on time and within budget.
Using a formal, structured process to handle foreseen and unforeseen project risk events minimizes surprises, costs, schedule delays, stress, and misunderstandings. Ultimately successful risk management requires an organizational culture in which threats are embraced not denied and problems are identified not hidden.

## Slide 3: Risk Management Process
Risk
  Uncertain or chance events that planning can not overcome or control.
Risk Management
  A proactive attempt to recognize and manage internal events and external threats that affect the likelihood of a project’s success.
    What can go wrong (risk event).
    How to minimize the risk event’s impact (consequences).
    What can be done before an event occurs (anticipation).
    What to do when an event occurs (contingency plans).
Notes: Risk is an uncertain event or condition (a cause) that, if it occurs, has a positive or negative effect (consequence) on project objectives. Risk management attempts to recognize risk events and manage or develop contingencies to control their effects when the project is implemented.

## Slide 4: The Risk Event Graph
FIGURE 7.1
Notes: Figure 7.1 presents a graphic model of the risk management challenge during the project life cycle. The chances of a risk event occurring (e.g., an error in time estimates, cost estimates, or design technology) are greatest due to uncertainty that attends early stages of a project.. As the project reaches its later stages, risk declines as uncertainties are resolved. However, the consequences of a risk event increase in cost over the life of the project as it becomes more difficult to alter fully developed project features.

## Slide 5: Risk Management’s Benefits
A proactive rather than reactive approach.
Reduces surprises and negative consequences.
Prepares the project manager to take advantage of appropriate risks.
Provides better control over the future.
Improves chances of reaching project performance objectives within budget and on time.
Notes: Risk management is a proactive approach rather than reactive that ensures surprises are reduced and negative consequences of undesirable events are minimized. It also prepares the project manager to take action when a time, cost, and/or technical advantage is possible. Project risk management controls for present and future risk to improve management’s chances of reaching project objectives on time, budget, and technical performance.

## Slide 6: The Risk Management Process
FIGURE 7.2
Notes: Figure 7.2 depicts the four steps of the risk management process. Step 1 entails identification of the sources of risk. Step 2 involves the assessment of the severity, likelihood of occurrence, and controllability of risks. Step 3 is focused on development of strategic and contingency plans for reducing and handling risks. Step 4 looks at the implementation of risk management strategy.

## Slide 7: Managing Risk
Step 1: Risk Identification
  Generate a list of possible risks through brainstorming, problem identification and risk profiling.
    Macro risks first, then specific events
Step 2: Risk Assessment
  Scenario analysis for event probability and impact
  Risk assessment matrix
  Failure Mode and Effects Analysis (FMEA)
  Probability analysis
    Decision trees, NPV, and PERT
  Semiquantitative scenario analysis
Notes: Step 1 in managing risk is risk identification which involves generating a list of possible risks through brainstorming, problem identification and risk profiling. Typically, macro risks that can affect the whole project as opposed to a specific section of the project or network are considered first and then specific events.
Step 2 in managing risk is risk assessment in which scenario analysis is used to estimate risk event probabilities and their impact. Various methods used in this step are:
  Risk assessment matrix
  Failure Mode and Effects Analysis (FMEA)
  Probability analysis
  Decision trees, NPV, and PERT
  Semiquantitative scenario analysis

## Slide 8: The Risk Breakdown Structure (RBS)
FIGURE 7.3
Notes: Figure 7.3 provides a generic example of a risk breakdown structure (RBS ) that used in conjunction with work breakdown structures (WBSs) to help management teams identify and eventually analyze risks during Step 1 of risk management.

## Slide 9: Partial Risk Profile for Product Development Project
FIGURE 7.4
Notes: Figure 7.4 provides a partial example of a risk profile. A risk profile is a list of questions that address traditional areas of uncertainty on a project. These questions have been developed and refined from previous, similar projects.

## Slide 10: Defined Conditions for Impact Scales of a Risk on Major Project Objectives (Examples for negative impacts only)
FIGURE 7.5
Notes: Figure 7.5 provides an example of how impact scales could be defined given the project objectives of cost, time, scope, and quality. The impact scales offer relative assessments of how risks affect project objectives.

## Slide 11: Risk Assessment Form
FIGURE 7.6
Notes: Figure 7.6 is a partial example of a risk assessment form used on an IS project involving the upgrade from Windows 7 to Windows 8. In addition to evaluating the severity and probability of risk events, The form assesses when the event might occur and its detection difficulty.
Detection difficulty is a measure of how easy it would be to detect that the event was going to occur in time to take mitigating action, that is, how much warning would the project manager have? In example, the detection scale would range from 5 (no warning) to 1 (lots of time to react).

## Slide 12: Risk Severity Matrix
FIGURE 7.7
Failure Mode and Effects Analysis (FMEA) Impact × Probability × Detection = Risk Value
 |  | User Backlash | Interface problems | 
 |  |  |  | System freezing
 |  |  |  | Hardware malfunc-tioning
Likelihood
Impact
Red zone (major risk)
Yellow zone (moderate risk)
Green zone (minor risk)
5
5
4
4
3
3
2
2
1
1
Notes: The risk matrix presented in Figure 7.7 consists of a 5 3 5 array of elements with each element representing a different set of impact and likelihood values. The matrix is divided into red, yellow, and green zones representing major, moderate, and minor risks, respectively. The red zone is centered on the top right corner of the matrix (high impact/high likelihood), while the green zone is centered on the bottom left corner (low impact/low likelihood). The moderate risk, yellow zone extends down the middle of the matrix.

## Slide 13: Managing Risk (cont’d)
Step 3: Risk Response Development
  Mitigating Risk
    Reducing the likelihood an adverse event will occur.
    Reducing impact of adverse event.
  Avoiding Risk
    Changing the project plan to eliminate the risk or condition.
  Transferring Risk
    Paying a premium to pass the risk to another party.
    Requiring Build-Own-Operate-Transfer (BOOT) provisions.
  Retaining Risk
    Making a conscious decision to accept the risk.
Notes: Step 3 involves developing responses to risks. Possible responses to risk events include:
  Mitigating risk by either reducing the likelihood an adverse event will occur or reducing impact of adverse event.
  Avoiding risk by changing the project plan to eliminate the risk or condition.
  Transferring risk by either paying a premium to pass the risk to another party or requiring Build-Own-Operate-Transfer (BOOT) provisions.
  Retaining risk by making a conscious decision to accept the risk.

## Slide 14: Contingency Planning
Contingency Plan
  An alternative plan that will be used if a possible foreseen risk event actually occurs.
  A plan of actions that will reduce or mitigate the negative impact (consequences) of a risk event.
Risks of Not Having a Contingency Plan
  Having no plan may slow managerial response.
  Decisions made under pressure can be potentially dangerous and costly.
Notes: Contingency planning involves developing an alternative plan that will be used if a possible foreseen risk event actually occurs to reduce or mitigate the negative impact (consequences) of a risk event.
Risks of not having a contingency plan include:
Having no plan which may slow managerial response.
Decisions made under pressure that can be potentially dangerous and costly.

## Slide 15: Risk Response Matrix
FIGURE 7.8
Notes: Figure 7.8 shows a risk response matrix for the Windows 8 that summarizes how the project team plans to manage risks that have been identified. The first step is to identify whether to reduce, share, transfer, or accept each risk. The next step is to identify a contingency plan (response) for each risk if that risk is triggered (occurs).

## Slide 16: Risk and Contingency Planning
Technical Risks
  Backup strategies if chosen technology fails.
  Assessing whether technical uncertainties can be resolved.
Schedule Risks
  Use of slack increases the risk of a late project finish.
  Imposed duration dates (absolute project finish date)
  Compression of project schedules due to a shortened project duration date.
Notes: Technical risks require backup strategies if chosen technology fails. Project managers must continually assess whether technical uncertainties can be resolved.
Schedule risks arise when the use of slack increases the risk of a late project finish, imposed duration dates (absolute project finish date) leave no room for delays, and project schedules become compressed due to a shortened project duration date.

## Slide 17: Risk and Contingency Planning (cont’d)
Costs Risks
  Time/cost dependency links: costs increase when problems take longer to solve than expected.
  Price protection risks (a rise in input costs) increase if the duration of a project is increased.
Funding Risks
  Changes in the supply of funds for the project can dramatically affect the likelihood of implementation or successful completion of a project.
Notes: For long-duration projects, risks of changes in resource costs increase when problems take longer to solve than expected. Price protection risks (a rise in input costs) increase if the duration of a project is increased.
Funding risks reflect how increased risks associated with changes in the supply of funds for the project can dramatically affect the likelihood of implementation or successful completion of a project.

## Slide 18: Opportunity Management Tactics
Exploit
  Seeking to eliminate the uncertainty associated with an opportunity to ensure that it definitely happens.
Share
  Allocating some or all of the ownership of an opportunity to another party who is best able to capture the opportunity for the benefit of the project.
Enhance
  Taking action to increase the probability and/or the positive impact of an opportunity.
Accept
  Being willing to take advantage of an opportunity if it occurs, but not taking action to pursue it.
Notes: Project managers can use several tactics to exploit an opportunity (take advantage of a positive risk by:
Taking exploitive actions that ensure the elimination of the uncertainty associated with an opportunity so that it definitely happens.
Sharing or allocating some or all of the ownership of an opportunity to another party who is best able to capture the opportunity for the benefit of the project.
Taking action to enhance the probability and/or the positive impact of an opportunity.
Being willing to accept taking advantage of an opportunity if it occurs, but not taking action to pursue it.

## Slide 19: Contingency Funding and Time Buffers
Contingency Funds
  Funds to cover project risks—identified and unknown.
    Size of funds reflects overall risk of a project
  Budget reserves
    Are linked to the identified risks of specific work packages.
  Management reserves
    Are large funds to be used to cover major unforeseen risks (e.g., change in project scope) of the total project.
Time Buffers
  Amounts of time used to compensate for unplanned delays in the project schedule.
    Severe risk, merge, noncritical, and scarce resource activities
Notes: Contingency funds are used to cover project risks—both identified and unknown. The size of funds reflects overall risk of a project. Budget reserves are fund-based contingencies linked to the identified risks of specific work packages.
Management reserves are large funds to be used to cover major unforeseen risks (e.g., change in project scope) of the total project.
Time buffers represent amounts of time used to compensate for unplanned delays in the project schedule. The buffers are added to critical project events that have severe risk severity, can be delayed due to waiting, noncritical events not on the critical path, and that use scarce resource activities

## Slide 20: Contingency Fund Estimate ($000s)
TABLE 7.1
Notes: Table 7.1 shows the development of a contingency fund estimate for a hypothetical project. This format helps keep budget and management reserves separate; budget control is also easily tracked using this format.

## Slide 21: Managing Risk (cont’d)
Step 4: Risk Response Control
  Risk control
    Execution of the risk response strategy
    Monitoring of triggering events
    Initiating contingency plans
    Watching for new risks
  Establishing a Change Management System
    Monitoring, tracking, and reporting risk
    Fostering an open organization environment
    Repeating risk identification/assessment exercises
    Assigning and documenting responsibility for managing risk
Notes: Step 4 in managing project risk involves:
  Exercising risk response control by
    Developing a risk register
    Execution of the risk response strategy
    Monitoring of triggering events
    Initiating contingency plans
    Watching for new risks
    Establishing a change management system for
      Monitoring, tracking, and reporting risk
      Fostering an open organization environment
      Repeating risk identification/assessment exercises
      Assigning and documenting responsibility for managing risk

## Slide 22: Change Management Control
Sources of Change
  Project scope changes
  Implementation of contingency plans
  Improvement changes
Notes: Coping with and controlling project changes present a formidable challenge for most project managers. Most changes fall into three categories:
Scope changes in the form of design or additions to the project represent big changes
Implementation of contingency plans, when risk events occur, represent changes in baseline costs and schedules.
Improvement changes suggested by project team members represent another category.

## Slide 23: Change Control System Process
Identify proposed changes.
List expected effects of proposed changes on schedule and budget.
Review, evaluate, and approve or disapprove of changes formally.
Negotiate and resolve conflicts of change, condition, and cost.
Communicate changes to parties affected.
Assign responsibility for implementing change.
Adjust master schedule and budget.
Track all changes that are to be implemented
Notes: Change management systems are designed to accomplish the following:
  Identify proposed changes.
  List expected effects of proposed change(s) on schedule and budget.
  Review, evaluate, and approve or disapprove changes formally.
  Negotiate and resolve conflicts of change, conditions, and cost.
  Communicate changes to parties affected.
  Assign responsibility for implementing change.
  Adjust master schedule and budget.
  Track all changes that are to be implemented.

## Slide 24: The Change Control Process
FIGURE 7.9
Notes: Figure 7.9 depicts the change control process as a flow diagram where the need for change originates, a change request is submitted, the request is reviewed, if approved, then the change is noted in the updated plan of record and distributed for action.

## Slide 25: Benefits of a Change Control System
Inconsequential changes are discouraged by the formal process.
Costs of changes are maintained in a log.
Integrity of the WBS and performance measures is maintained.
Allocation and use of budget and management reserve funds are tracked.
Responsibility for implementation is clarified.
Effect of changes is visible to all parties involved.
Implementation of change is monitored.
Scope changes will be quickly reflected in baseline and performance measures.
Notes: Benefits of a change control system are:
  Inconsequential changes are discouraged by the formal process.
  Costs of changes are maintained in a log.
  Integrity of the WBS and performance measures is maintained.
  Allocation and use of budget and management reserve funds are tracked.
  Responsibility for implementation is clarified.
  Effect of changes is visible to all parties involved.
  Implementation of change is monitored.
  Scope changes will be quickly reflected in baseline and performance measures.

## Slide 26: Sample Change Request
FIGURE 7.10
Notes: Figure 7.10 depicts an example of a simplified change request form.

## Slide 27: Change Request Log
FIGURE 7.11
Notes: Figure 7.1 presents an abridged version of a change request log for a construction project. These logs are used to monitor change requests. They typically summarize the status of all outstanding change requests and include such useful information as source and date of the change, document codes for related information, cost estimates, and the current status of the request.

## Slide 28: Key Terms
Avoiding risk
Budget reserve
Change management system
Contingency plan
Management reserve
Mitigating risk
Opportunity
Retaining risk
Risk
Risk breakdown structure (RBS)
Risk profile
Risk register
Risk severity matrix
Scenario analysis
Time buffer
Transferring risk
Notes: Avoiding risk is the elimination of the risk cause before the project begins.
Budget reserve covers identified risks that may occur and influence baseline tasks or costs.
Change management system creates a defined process for authorizing and documenting changes in the scope of a project.
Contingency plan covers possible identified project risks that may materialize over the life of the project.
Management reserve is a percentage of the total project reserved as a risk-reduction contingency measure to cover unforeseen, new problems—not unnecessary overruns.
Mitigating risk involves taking action to either reduce the likelihood that a risk will occur and/or the impact the risk will have on the project.
Risk is the chance that an undesirable project event will occur and the consequences of all its possible outcomes.
Risk breakdown structure (RBS) is a hierarchical depiction of the identified project risks arranged by risk category and subcategory that identifies the various areas and causes of potential risks.
Risk profile is a list of questions that addresses traditional areas of uncertainty on a project.
Risk severity matrix is a tool used to assess the impact of risks on a project.
Time buffer is a contingency amount of time for an activity to cover uncertainty—for example, availability of a key resource or merge event.
Transferring risk is shifting responsibility for a risk to another party.

## Slide 29: Appendix 7.1
PERT and PERT Simulation
Notes: In 1958 the Special Office of the Navy and the Booze, Allen, and Hamilton consulting firm developed PERT (program evaluation and review technique) to schedule the more than 3,300 contractors of the Polaris submarine project and to cover uncertainty of activity time estimates.

## Slide 30: PERT—Program Evaluation Review Technique
Assumes each activity duration has a range that statistically follows a beta distribution.
Uses three time estimates for each activity: optimistic, pessimistic, and a weighted average to represent activity durations.
  Knowing the weighted average and variances for each activity allows the project planner to compute the probability of meeting different project durations.
Notes: PERT is almost identical to the critical path method (CPM) technique except it assumes each activity duration has a range that follows a statistical distribution. PERT uses three time estimates for each activity. Basically, this means each activity duration can range from an optimistic time to a pessimistic time, and a weighted average can be computed for each activity.

## Slide 31: Activity and Project Frequency Distributions
FIGURE A7.1
Notes: Figure A7.1A depicts a beta distribution for activity durations that is skewed toward the right and is representative of work that tends to stay late once it is behind. The distribution for the project duration is represented by a normal (symmetrical) distribution shown in Figure A7.1B. The project distribution represents the sum of the weighted averages of the activities on the critical path(s).

## Slide 32: Activity Time Calculations
The weighted average activity time is computed by the following formula:
(7.1)
Notes: Knowing the weighted average and variances for each activity allows the project planner to compute the probability of meeting different project durations.

## Slide 33: Activity Time Calculations (cont’d)
The variability in the activity time estimates is approximated by the following equations:
The standard deviation for the activity:
The standard deviation for the project:
Note the standard deviation of the activity is squared in this equation; this is also called variance. This sum includes only activities on the critical path(s) or path being reviewed.
(7.2)
(7.3)
Notes: Equation 7.2 represents the standard deviation for the activity. Equation 7.3 represents the standard deviation for the project. Note the standard deviation of the activity is squared in this equation; this is also called variance. This sum includes only activities on the critical path(s) or path being reviewed.

## Slide 34: Activity Times and Variances
TABLE A7.1
Notes: The activity times and variances for a hypothetical example using the PERT technique are given in Table A7.1.

## Slide 35: Probability of Completing the Project
The equation below is used to compute the “Z” value found in statistical tables (Z = number of standard deviations from the mean), which, in turn, tells the probability of completing the project in the time specified.
(7.4)
Notes: Equation 7.4 is used to compute the “Z” value found in statistical tables (Z = the number of standard deviations from the mean), which, in turn, tells the probability of completing the project in the time specified.

## Slide 36: Hypothetical Network
FIGURE A7.2
Notes: The project network is presented in Figure A7.2. This figure shows the project network as AOA and AON. The AON network is presented as a reminder that PERT can use AON networks as well as AOA.

## Slide 37: Hypothetical Network (cont’d)
FIGURE A7.2 (cont’d)
Notes: The project network is presented in Figure A7.2. This figure shows the project network as AOA.

## Slide 38: Possible Project Duration
Probability project is completed before scheduled time (TS) of 67 units
Probability project is completed by the 60th unit time period (TS)
FIGURE A7.3
Notes: The normal curve for the project network presented in Figure A7.2 would appear as shown in Figure A7.3.

## Slide 39: Z Values and Probabilities
TABLE A7.2
Notes: Table A7.2 presents Z values and associated probabilities for calculating the probability of project completion times.